## Planning
taskID | task | predecessorTaskIDs | mostLikelyHours | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 8 | 8 | 11 | 24 | x
B | Develop marketing strategy |  | 20 | 16 | 21 | 32 | x
C | Design brochure | A | 10 | 8 | 12 | 24 | x
D | Develop product prototype
D1 | Requirements analysis | A | 16 | 16 | 19 | 32 |  | x | x | x | x
D2 | Software design | D1 | 60 | 40 | 60 | 80 |  | x | x | x | x
D3 | System design | D1 | 60 | 40 | 60 | 80 |  | x | x | x | x
D4 | Coding | D2, D3 | 100 | 80 | 100 | 120 |  | x | x | x | x
D5 | Write documentation | D4 | 32 | 16 | 32 | 48 |  | x | x | x | x
D6 | Unit testing | D4 | 40 | 24 | 41 | 60 |  | x | x | x | x
D7 | System testing | D6 | 40 | 24 | 41 | 60 |  | x | x | x | x
D8 | Package deliverables | D5, D7 | 16 | 8 | 16 | 24 |  | x | x | x | x
E | Survey potential market | B, C | 32 | 19 | 33 | 48 | x
F | Develop pricing plan | D8, E | 16 | 8 | 16 | 24 | x |  | x | x
G | Develop implementation plan | A, D8 | 24 | 24 | 27 | 40 | x | x | x | x | x
H | Write client proposal | F, G | 16 | 16 | 19 | 32 | x

## Cost Analysis
Cost per Hour
Project Manager | 75
Fronted Developer | 70
Backend Developer | 70
Data Scientist | 90
Data Engineer | 90
Role | Hours Worked | Cost
Developer Hours | 504
Frontend Developer | 126 | 8820
Backend Developer | 126 | 8820
Data Scientist | 126 | 11340
Data Engineer | 126 | 11340
Other Hours | 240
Project Manager | 240 | 18000
| Total Cost | 58320