## best_scenario
PROJECT: Recommendation System
Assignment Two |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Albert Olea
Project start date: | 2025-02-02 |  |  |  |  | February | [27 empty] | March
Scrolling increment: | 1 | time axis 2025-02-03 to 2025-03-30
Milestone description | Type | Task ID | Predecessor Task ID | Start | Days | time axis 2025-02-03 to 2025-03-30
Best Case Scenario
Describe product | On Track | A |  | 2025-02-03 | 1
Develop marketing strategy | Low Risk | B |  | 2025-02-03 | 3
Design brochure | Low Risk | C | A | 2025-02-04 | 1
Develop product prototype |  | D
Requirements analysis | Med Risk | D1 | A | 2025-02-05 | 3
Software design | Low Risk | D2 | D1 | 2025-02-07 | 4
System design | Med Risk | D3 | D1 | 2025-02-07 | 4
Coding | High Risk | D4 | D2, D3 | 2025-02-11 | 16
Write documentation | Low Risk | D5 | D4 | 2025-02-27 | 4
Unit testing | Med Risk | D6 | D4 | 2025-02-27 | 6
System testing | Low Risk | D7 | D6 | 2025-03-05 | 3
Package deliverables | High Risk | D8 | D5, D7 | 2025-03-08 | 3
Survey potential market | Med Risk | E | B, C | 2025-02-06 | 4
Develop pricing plan | High Risk | F | D8, E | 2025-03-11 | 4
Develop implementation plan | High Risk | G | A, D8 | 2025-03-11 | 2
Write client proposal | Med Risk | H | F, G | 2025-03-15 | 2
Linear Programming Model Critical Path
Task | start | end | hours total | days total | start day
Describe product | 0 | 8 | 8 | 1 | 0
Develop marketing strategy | 0 | 24 | 24 | 3 | 0
Design brochure | 8 | 16 | 8 | 1 | 1
Develop product prototype
Requirements analysis | 8 | 32 | 24 | 3 | 1
Software design | 32 | 64 | 32 | 4 | 4
System design | 32 | 64 | 32 | 4 | 4
Coding | 64 | 192 | 128 | 16 | 8
Write documentation | 192 | 224 | 32 | 4 | 24
Unit testing | 192 | 240 | 48 | 6 | 24
System testing | 240 | 264 | 24 | 3 | 30
Package deliverables | 264 | 288 | 24 | 3 | 33
Survey potential market | 24 | 56 | 32 | 4 | 3
Develop pricing plan | 288 | 320 | 32 | 4 | 36
Develop implementation plan | 288 | 304 | 16 | 2 | 36
Write client proposal | 320 | 336 | 16 | 2 | 40

## worst_scenario
PROJECT: Recommendation System
Assignment Two |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Albert Olea
Project start date: | 2025-02-02 |  |  |  |  | February | [27 empty] | March
Scrolling increment: | 1 | time axis 2025-02-03 to 2025-03-30
Milestone description | Type | Task ID | Predecessor Task ID | Start | Days | time axis 2025-02-03 to 2025-03-30
Worst Case Scenario
Describe product | On Track | A |  | 2025-02-03 | 2
Develop marketing strategy | Low Risk | B |  | 2025-02-03 | 4
Design brochure | Low Risk | C | A | 2025-02-05 | 2
Develop product prototype |  | D
Requirements analysis | Med Risk | D1 | A | 2025-02-07 | 4
Software design | Low Risk | D2 | D1 | 2025-02-09 | 6
System design | Med Risk | D3 | D1 | 2025-02-09 | 6
Coding | High Risk | D4 | D2, D3 | 2025-02-15 | 20
Write documentation | Low Risk | D5 | D4 | 2025-03-07 | 6
Unit testing | Med Risk | D6 | D4 | 2025-03-07 | 8
System testing | Low Risk | D7 | D6 | 2025-03-15 | 4
Package deliverables | High Risk | D8 | D5, D7 | 2025-03-19 | 4.5
Survey potential market | Med Risk | E | B, C | 2025-02-07 | 6
Develop pricing plan | High Risk | F | D8, E | 2025-03-23 12:00 | 5
Develop implementation plan | High Risk | G | A, D8 | 2025-03-23 12:00 | 3
Write client proposal | Med Risk | H | F, G | 2025-03-28 12:00 | 3
Linear Programming Model Critical Path
Task | start | end | hours total | days total | start day
Describe product | 0 | 16 | 16 | 2 | 0
Develop marketing strategy | 0 | 32 | 32 | 4 | 0
Design brochure | 16 | 32 | 16 | 2 | 2
Develop product prototype
Requirements analysis | 16 | 48 | 32 | 4 | 2
Software design | 48 | 96 | 48 | 6 | 6
System design | 48 | 96 | 48 | 6 | 6
Coding | 96 | 256 | 160 | 20 | 12
Write documentation | 256 | 304 | 48 | 6 | 32
Unit testing | 256 | 320 | 64 | 8 | 32
System testing | 320 | 352 | 32 | 4 | 40
Package deliverables | 352 | 388 | 36 | 4.5 | 44
Survey potential market | 32 | 80 | 48 | 6 | 4
Develop pricing plan | 388 | 428 | 40 | 5 | 48.5
Develop implementation plan | 388 | 412 | 24 | 3 | 48.5
Write client proposal | 428 | 452 | 24 | 3 | 53.5

## expected_scenario
PROJECT: Recommendation System
Assignment Two |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Albert Olea
Project start date: | 2025-02-02 |  |  |  |  | February | [27 empty] | March
Scrolling increment: | 1 | time axis 2025-02-03 to 2025-03-30
Milestone description | Type | Task ID | Predecessor Task ID | Start | Days | time axis 2025-02-03 to 2025-03-30
Expected Case Scenario
Describe product | On Track | A |  | 2025-02-03 | 1.5
Develop marketing strategy | Low Risk | B |  | 2025-02-03 | 3.5
Design brochure | Low Risk | C | A | 2025-02-04 12:00 | 1.5
Develop product prototype |  | D
Requirements analysis | Med Risk | D1 | A | 2025-02-06 | 3.5
Software design | Low Risk | D2 | D1 | 2025-02-08 | 5
System design | Med Risk | D3 | D1 | 2025-02-08 | 5
Coding | High Risk | D4 | D2, D3 | 2025-02-13 | 18
Write documentation | Low Risk | D5 | D4 | 2025-03-03 | 5
Unit testing | Med Risk | D6 | D4 | 2025-03-03 | 7
System testing | Low Risk | D7 | D6 | 2025-03-10 | 3.5
Package deliverables | High Risk | D8 | D5, D7 | 2025-03-13 12:00 | 3.75
Survey potential market | Med Risk | E | B, C | 2025-02-06 12:00 | 4.5
Develop pricing plan | High Risk | F | D8, E | 2025-03-17 06:00 | 4
Develop implementation plan | High Risk | G | A, D8 | 2025-03-17 06:00 | 2.5
Write client proposal | Med Risk | H | F, G | 2025-03-21 06:00 | 2.5
Linear Programming Model Critical Path
Task | start | end | hours total | days total | start day
Describe product | 0 | 12 | 12 | 1.5 | 0
Develop marketing strategy | 0 | 28 | 28 | 3.5 | 0
Design brochure | 12 | 24 | 12 | 1.5 | 1.5
Develop product prototype
Requirements analysis | 12 | 40 | 28 | 3.5 | 1.5
Software design | 40 | 80 | 40 | 5 | 5
System design | 40 | 80 | 40 | 5 | 5
Coding | 80 | 224 | 144 | 18 | 10
Write documentation | 224 | 264 | 40 | 5 | 28
Unit testing | 224 | 280 | 56 | 7 | 28
System testing | 280 | 308 | 28 | 3.5 | 35
Package deliverables | 308 | 338 | 30 | 3.75 | 38.5
Survey potential market | 28 | 64 | 36 | 4.5 | 3.5
Develop pricing plan | 338 | 370 | 32 | 4 | 42.25
Develop implementation plan | 338 | 358 | 20 | 2.5 | 42.25
Write client proposal | 370 | 390 | 20 | 2.5 | 46.25